Project Charter Document

Project Name:	Optimized Equipment Utilization and management for IVF Laboratory Operations

Industry:           	Health care (IVF & Fertility Services)

Department:	Data Analysis

Product/Process:	Data Analysis

Prepared By

| Document Owner(s) | Project/Organization Role |
| --- | --- |
| Give your name | Mention that you are data analyst or data scientist |
| P. Sarath kumar | Data analyst |

Project Charter Version Control

| Version | Date | Author | Change Description |
| --- | --- | --- | --- |
| 1.0 | 16/12/2025 | P. Sarath kumar | Document created |

TABLE OF CONTENTS

1	PROJECT CHARTER PURPOSE	3

2	PROJECT EXECUTIVE SUMMARY	3

3	PROJECT OVERVIEW	4

4	PROJECT SCOPE	4

4.1	Project Deliverables	4

4.2	Deliverables Out of Scope	4

4.3	Project Duration (start date: 15/09/2021 End date: 05/10/2021)	4

5	PROJECT CONDITIONS	5

5.1	Project Assumptions	5

5.2	Project Issues – Fill it as and how project progresses.	5

5.3	Project Risks – Identify if there are any risks that you foresee.	6

6	PROJECT REFERENCES – Any previous projects you have referred. If yes, please share the details.	6

7	APPROVALS	6

# PROJECT CHARTER PURPOSE

The purpose of this project is to enhance the utilization and effective management of high value equipment IVF laboratory operations through data analysis. The project focuses on identifying issues such as equipment idle time, unplanned downtime and scheduling inefficiencies by analyzing equipment usage and operational data.

Using data driven insights and BI based reporting, the project aims to increase equipment utilization, reduce delays and downtime and control operational costs while ensuring smooth lab operations and better clinical results.

# PROJECT EXECUTIVE SUMMARY

- Business Problem:

IVF labs rely on high cost equipment such as incubators, microscopes and ICSI workstations yet utilization rates vary widely (40% – 85%), leading to 20 – 30% idle time, 10 – 15% work flow delays and 15 – 25% unnecessary operating costs. At the same time insufficient redundancy for critical procedures can cause 2 – 4 hour delays when equipment is unavailable, directly affecting embryo viability and clinic throughput.

- Business Objective:

Maximize utilization of high value IVF lab Equipment

- Business Constraint:

Minimize equipment down time and scheduling conflicts

- Success Criteria:

  - Business Success Criteria :

Increase average equipment utilization to ≥ 75 – 85% without exceeding safe workload limits.

  - Economic Success Criteria :

Lower operational costs linked to idle or redundant equipment by ≥ 10 – 15%.

- Data Collection: Update this section after the research is done.

- Scope: If you are doing this for any specific department of the organization then please mention the same.

Data analysis department.

- Assumptions: E.g., Data will be provided by customer, Cloud & GPU will be provided by customer

Data will be extracted from public sources and then client provided data is mapped

and finally one master data will be shared by Innodatatics for further analysis.

- Risks: E.g., Required data might not be available; Server connectivity might be weak, etc.

- Costs: Project cost – You can do assumptions by putting [number of hours * number of human resources (cadre wise) * hourly cost]

- Timeline: High level timeline of the project. E.g., Project will be for 20 to 25 days.

- Approach: Data Analytics Project Management Methodology

# PROJECT OVERVIEW

This project aims to improve the usage and management of equipment in IVF (In Vitro Fertilisation) laboratories. IVF labs use costly and critical equipment such as incubators, microscopes and ICIS (Intracytoplasmic Sperm Injection) workstations for important medical procedures. Due to poor planning and uneven usage, some equipment remains idle while others are overused, causing delays and increased operational costs.

The project proposes a centralized, data driven system to monitor equipment used and availability. This system helps in better scheduling, reducing downtime and improving overall workflow efficiency.

The objective of the project is to maximize equipment utilization, reduce delays and lower unnecessary operational costs, there by improving the performance of IVF laboratory operations.

# PROJECT SCOPE

## Project Deliverables

| Milestone | Deliverable |
| --- | --- |
| - Identifying Constraints and design the project architecture, explore various public forums to collect relevant data, Data Preparation. | - Deliverable 1.1—Identifying Constraints and design the project architecture. - Deliverable 1.2—Explore various public forums to collect relevant data. - Deliverable 1.3— Data Preparation |
| - EDA and Descriptive Analytics | - Deliverable 2.1— EDA and Descriptive Analytics - Deliverable 2.2— Insights documentation |
| - Show case and review, Final Presentation and documentation, Handover and KT. | - Deliverable3.1 – show case and review. - Deliverable3.2 – Final Presentation and documentation - Deliverable3.3 – Handover and KT |

## Deliverables Out of Scope

- Web Application

- Mobile App

- Cloud based deployment

## Project Duration (start date: 15/12/2025 End date: 15/01/2025)

| Project Milestone | Date Estimate | Deliverable(s) Included | Confidence Level |
| --- | --- | --- | --- |
| - Identifying Constraints and design the project architecture, explore various public forums to collect relevant data, Data Preparation. | [15/12/2025] - [21/12/2025] | - Deliverable 1.1—Identifying Constraints and design the project architecture. - Deliverable 1.2—Explore various public forums to collect relevant data. - Deliverable 1.3— Data Preparation | [High] |
| - EDA and Descriptive Analytics | [22/12/2025] - [31/12/2025] | - Deliverable 2.1— EDA and Descriptive Analytics - Deliverable 2.2--- Insights documentation | [High] |
| - Show case and review, Final Presentation and documentation, Handover and KT. | [01/01/2026] - [05/01/2026] | - Deliverable3.1 – show case and review - Deliverable3.2 – Final Presentation and documentation - Deliverable3.3 – Handover and KT | [Medium] |

# PROJECT CONDITIONS

## Project Assumptions

- Data will be extracted from public sources and then client provided data is mapped and finally one master data will be shared by Innodatatics for further analysis.

- Dashboards and insights are mandatory.

## Project Issues – Fill it as and how project progresses.

Priority Criteria

1 − High-priority/critical-path issue; requires immediate follow-up and resolution.

2	 − Medium-priority issue; requires follow-up before completion of next project milestone.

3	 − Low-priority issue; to be resolved prior to project completion.

4 − Closed issue.

| # | Date | Priority | Owner | Description | Status & Resolution |
| --- | --- | --- | --- | --- | --- |
| 1 |  | High |  |  |  |
| 2 |  | High |  |  |  |

## Project Risks – Identify if there are any risks that you foresee.

| # | Risk Area | Likelihood | Risk Owner | Project Impact-Mitigation Plan |
| --- | --- | --- | --- | --- |
| 1 | [Project Risk] | [High/Medium/Low] |  |  |
| 2 | [Project Risk] | [High/Medium/Low] |  |  |

# PROJECT REFERENCES – Any previous projects you have referred. If yes, please share the details.

| Project | Description |
| --- | --- |
| [ - NA - | - NA - |

# APPROVALS

Prepared by	P.Sarath kumar_____________________

Project Manager

Approved by	Bharani Kumar.D___________________

Project Sponsor

__________________________________

Executive Sponsor

__________________________________

Client Sponsor